## Instructions
INSTRUCTIONS FOR COMPLETING
UVA HECO-11 and HECO-11a FORMS
I. GENERAL INSTRUCTIONS
Please read all instructions carefully before using this spreadsheet to create the HECO-11 and HECO-11a forms.
Macros must be "enabled" to take advantage of some of the time-saving features incorporated within this template.
( In order for macros to run in Excel, the Excel macro security setting must be set to "Medium". To adjust this
setting, go to Tools / Macro / Security on the Excel menubar and adjust security setting to "Medium". You may
need to exit Excel once and then re-open Excel for the new security setting to take effect.)
Excel/Office 2007 users may need to save this as a "Macro-Enabled Worksheet".
This spreadsheet contains a number of built-in calculations to simplify the creation of HECO-11 and HECO-11a forms.
To ensure the integrity of the data, please do not attempt to modify the spreadsheet. Areas where data
can be entered are highlighted in yellow.
It is recommended that the user print a copy of this instruction sheet to use as a reference when completing
these forms.
The various Parts of the HECO-11 and HECO-11a are accessed by clicking on the blue tabs at the bottom of the screen.
|  | Use the tab key to move forward to the next fillable field. |  | ¦----->
|  | Use the shift-tab to move backwards to the previous fillable field. |  | <-----¦
(You can also use the mouse and cursor keys to navigate, but the tab key is generally the most efficient means.)
Some fields have "drop-down" selection arrows on the right side of the field. For these
types of fields, click on the arrow, then select an appropriate choice from the list.
Click on the tabs at the bottom of this file to go to the appropriate page.
THE CHANGE ORDER LOG ( "CO Log" tab )
The most important part of this spreadsheet is the "Contract Summary and Change Order Log".
The "Contract Summary" contains general project information, a running tally of all approved change orders, and the
original and current contract costs and completion dates.
The "Change Order Log" lists the key cost and schedule data for each change order and also identifies
if approval by the Authorized Designee is required.
The information entered in the Contract Summary and Change Order Log is used to automatically complete portions of
the HECO-11 and HECO-11a forms for the Change Order number entered on the "HECO-11 Part 1" sheet.
Specifically, the general information from the Contract Summary and Change Order Log is used to automatically complete:
- HECO-11, Part 1 (Fully completes Part 1.)
- HECO-11, Part 2 (Completes the header information. Remaining portions must be completed by user.)
- HECO-11a, All Parts (Completes the header information. Remaining portions must be completed by user.)
This built-in automation was designed to save users from redundant keying of data and to eliminate math and transposition errors.
When entering data in the Change Order Log, always enter the change orders sequentially, starting with the lowest number change order.
( Do not leave a blank line between change orders or erroneous totals may result ! )
Always update the Contract Summary and Change Order Log first, before completing and generating the HECO-11 and HECO-11a.
IF YOU WISH TO RETAIN DETAILED INFORMATION FOR EACH CHANGE ORDER, DO THE FOLLOWING:
Before beginning each new HECO-11, make a copy of the spreadsheet. (Do a "Save as" and name the new version
of the spreadsheet: "Change Order Number XX", substituting for "XX" the number of the next Change Order to be created.)
While the Change Order Log will list summary information for all Change Orders to date, only the detailed information (i.e., the HECO-11
and HECO-11a) for one change order number is saved in the spreadsheet. ( The spreadsheet is not meant to be a repository
of all HECO-11 and HECO-11a forms. It is intended to be used to create, save, and print information for the latest HECO-11 and HECO-11a.)
II. STEP-BY-STEP INSTRUCTIONS
Change Order Log
1 |  | Save a copy of the previous Change Order spreadsheet file and name it as noted in the preceding paragraph.
2 |  | Click on the "Contract Summary and Change Order Log" tab.
3 |  | In the "Contract Summary" section, enter new (or verify existing) data for the cells hignlighted in yellow.
4 |  | In the "Change Order Log" section, enter the following information:
| - | Change Order Number
- Change Order Numbers are sequential integer numbers. Start with "1".
- Enter change orders sequentially in the log - starting with the lowest number change order.
(See the note below for projects aready in progess.)
- Don't skip rows between change orders (i.e., don't leave any blank rows between
change order entries) or else erroneous results will occur.
| - | Change Order Date (enter in mm/dd/yy format)
| - | Change Order Amount (enter the total value of latest Change Order)
| - | Schedule Extension (enter the additional number of days the contract will be extended due to latest Change Order)
( All other information shown on the log is computed automatically and is used elsewhere in the spreadsheet. )
NOTE: If this spreadsheet is being implemented for a project already in progress, there are two options for
entering Change Orders which were issued prior to this new spreadsheet becoming available:
a) Enter all Change Orders as individual line items in the Log (recommended method), or
b) Group all Change Orders already executed under one line entry. After this
one "catch up entry", enter all subsequent Change Orders as individual line items.
5 |  | Print a copy of the Log, if desired, using the File/Print menu command. ( To limit the number of pages printed,
enter the appropriate page numbers in the "Pages" section of the "Print Range" dialog box. )
HECO-11 Part 1, Construction Change Order (Summary of Work)
Part 1 of the HECO-11 lists the summary cost and contract completion information related to the current change,
the cumulative cost and completion data, and provides signature lines for all affected parties.
1 |  | Enter the specific Change Order Number for which you wish to create a HECO-11 and HECO-11a. No other input is required
as all other information for this sheet is derived from the Contract Summary and Change Order Log.
(NOTE: The Contract Summary and Change Order Log must be complete for all Change Orders up to and including
this Change Order.)
2 |  | Print a copy of the HECO-11 Part 1 using the File/Print menu command or the printer icon. (You can also use the Print
or Print Preview buttons on the toolbar below.)
HECO-11 Part 2, Construction Change Order (Itemization of Work)
Part 2 of the HECO-11 provides an itemized breakdown of the scope of work to be performed.
1 |  | Enter the required data for the each of the five columns highlighted in yellow. Additional data entry instructions
are provided as each cell is selected.
2 |  | Once all detail line items have been entered, verify that the sum of all detail line items match the total amount
entered earlier in the Change Order Log for this Change Order. If the amount in the Change Order Log and the sum of the Part 2 detail
entries do not match, an error message will appear in red at the top of the Part 2 sheet. Correct either the detail amounts in Part 2
or the total amount entered in the Change Order Log, as needed. Once the amounts match, the error message will clear.
3 |  | An asterisk ( * ) appearing adjacent to the amount field on Part 2, denotes that either the "Initiated By" or
the "Reason for Change" fields, or both, were not completed properly. ( An entry must appear in both of these
fields, if an associated dollar amount was entered.) Fill in these fields with the appropriate entries to clear these
error flags.
4 |  | Once the errors described in 2 and 3 above have been corrected, print a copy of this sheet using the File/Print
menu command. To limit the number of pages printed, enter the appropriate page numbers in the "Pages"
section of the "Print Range" dialog box.
HECO-11a Part 1, Change Order Justification ( A/E's Justification )
Part 1 of the HECO-11a is completed by the A/E to:
- provide a brief narrative summary of work to be performed
- explain why the change is required
- identify the A/E's recommendation to the Agency
1 |  | Describe the work.
2 |  | Describe why change is required.
3 |  | Use the drop-down arrow to select either "Recommend Approval" or "Recommend Disapproval".
4 |  | Print out the HECO-11a Part 1 and obtain signature of the authorized A/E representative.
HECO-11a Part 2, Change Order Justification ( Agency's Justification )
Part 2 of the HECO-11a is completed by the Agency to:
- verify that adequate contingency is available
- identify cost sharing arrangements for design errors or omissions
- justify Change Orders which are a result of a change in agency requirements
1 |  | Enter the latest APPROVED CO-8 Contingency amount.
If sufficient contingency is available to accommodate this Change Order, the balance remaining
after approval of this Change Order will be displayed.
If the contingency balance is insufficient, the minimum amount of additional contingency required to
accommodate this Change Order will be displayed. Submit a revised CO-8 concurrent with the Change
Order to increase the construction change order contingency amount.
2 |  | Complete the two items of information needed for Change Orders which involve "design errors and omissions".
3 |  | Complete the four items of information needed for Change Orders which involve "changes in agency requirements".
4 |  | Print out the HECO-11a Part 1 and obtain signature of the authorized Agency representative.
HECO-11a Part 3, Change Order Justification ( Agency's Justification )
Part 3 of the HECO-11a is a statistical summary compiled automatically from the entries on Part 2 of the HECO-11.
1 |  | Verify that the total on this sheet matches the total Change Order amount. If the total on this sheet is
incorrect, return to Part 2 of the HECO-11 sheet and ensure that all lines with an "Amount" have a corresponding
"Reason Code".
2 |  | Once correct, print out a copy of this sheet.
III. SIGNATURE/APPROVAL REQUIREMENTS (HECO-11 Part 1)
1 |  | All change orders require the following signatures:
* Authorized A/E Representative
* Authorized Contractor Representative
* Authorized Agency Representative
2 |  | Approval of the Chief Facilities Officer is required for Change Orders that:
Are greater than $50,000, or
Where the resulting cumulative sum of all Change Orders exceeds 25% of the original Contract Amount
FINAL NOTES:
The Log and Contract Summary were added to assist agencies in preventing math errors, eliminating redundant data entry,
and in automatically flagging when approval by the Governor's Designee is required.

## CO Log
CONTRACT SUMMARY: | [5 empty] | Project: 0 - 00000 - 000 |  |  | Enter applicable data in the
[7 empty] | PIMS Project: |  | cells highlighted in yellow.
WO#:
|  | Code Number | Description
Agency: |  | 0 | ***** Please enter an Agency Code ***** | [5 empty] | Please be certain to
Project: |  | 00000 | [6 empty] | fill out both the adjacent
Sub-Project: |  | 000 | [6 empty] | "Contract Summary" and
Location of the Work: | [8 empty] | the "Change Order Log"
Contractor Name: | [8 empty] | before proceeding to the
Architect/Engineer: | [8 empty] | CO-11 and the CO-11a
forms, proper.
Contract #: |  |  |  |  | Original Contract | 100000 | PO #
Date Contract Ratified: |  |  |  |  | Additive Changes | 0 |  |  | The data from the
Original Contract Completion Date: |  |  |  |  | Deductive Changes | 0 |  |  | "Change Order Log"
Cumulative Schedule Extensions: |  |  | 0 | days | Total Changes | 0 | 0% |  | is used to generate
Revised Contract Completion Date: |  |  | 0 |  | Revised Contract | 100000 |  |  | much of the data on
the CO-11 form.
CHANGE ORDER LOG: | [8 empty] | Scroll down to view / edit
|  | Updated thru Change Order Number: | 0 | [5 empty] | the "Change Order Log".
[7 empty] | Cumul. | Revised
Change | Change | Change | Schedule | Authorized | Cumulative | Revised | Schedule | Contract
Order | Order | Order | Extension | Approval | Change | Contract | Extension | Completion
Number | Date | Amount | (days) | Required? | Orders | Value | (days) | Date
[5 empty] | 0 |  | 0

## HECO-11_Part 1
The only item which MUST be entered on this sheet is the "Change Order Number". Be sure to first
enter all data on the "Contract Summary AND Change Order Log". ( This is necessary as the data
from the "Contact Summary and Change Order Log" is used to generate this Change Order sheet. )
[5 empty] | CONTRACT CHANGE ORDER | [12 empty] | HECO-11
(Rev. 08/31/12) |  |  |  |  | ( Summary of Work ) | [12 empty] | Part 1
Project Code | [9 empty] | Change Order Number |  |  |  |  | Change Order Date
0 - 00000 - 000 | [14 empty] | #N/A
|  |  |  | Code |  | Description
Agency: |  |  |  | 0 |  | ***** Please enter an Agency Code *****
Project: |  |  |  | 00000 |  | 0
Sub-Project: |  |  |  | 000
PIMS #: |  |  | 0 |  |  |  | WO #: |  | 0 |  | Purchase Order # |  | 0
To: |  | 0
| Address: | [10 empty] | City/State:
Under your contract dated December 30, 1899 for work at
0
#N/A
|  | the Contract Price, in accordance with the Contract Documents, the sum of | [13 empty] | #N/A
#VALUE!
#N/A
#N/A
(Failure to include a change for time shall waive any change to the time allowed by the Contract for completion of the
Work unless the parties mutually agree in writing to postpone a determination of the change to time resulting from the
Change Order. Such determination may not be postponed more than 45 days from the approval of this Change Order
by the agency.)
| CONTRACT COST SUMMARY | [10 empty] | CONTRACT SCHEDULE SUMMARY
| (inclusive of this Change Order) | [10 empty] | (inclusive of this Change Order)
| Original Contract Amount | [6 empty] | 100000 |  |  |  | Original Contract Completion Date: |  |  |  |  | 0
| Cumulative Changes Orders | [6 empty] | #N/A |  |  |  | Cumulative Schedule Extension: |  |  |  |  | #N/A
| Revised Contract Amount | [6 empty] | #N/A |  |  |  | Revised Contract Completion Date: |  |  |  |  | #N/A
CHANGE AUTHORIZATION
Issued By:
[10 empty] | Authorized A/E Representative | [7 empty] | Date
Accepted By:
[10 empty] | Authorized Contractor Representative | [7 empty] | Date
Approved / Recommended By:
[10 empty] | Authorized Agency Representative | [7 empty] | Date
Approval by the Chief Facilities Officer is required for each Change Order if: 1) change order amount is > $50,000, or 2) the resulting cumulative sum of all Change Orders exceeds 25% of the original Contract Amount
#N/A
| Approved By: | [12 empty] | Donald E. Sundgren
[10 empty] | Chief Facilities Officer | [7 empty] | Date
Note on AE56: Drop down box w/ Printed authorized name
Note on AE68: Drop down box w/ Printed authorized name
The only item which MUST be entered on this sheet is the "Change Order Number"

## HECO-11_Part 2
|  |  | CONTRACT CHANGE ORDER |  |  |  | HECO-11 | A red asterisk ( * ) is a warning that either
(Rev. 08/31/12) |  |  | ( Itemization of Work ) |  |  |  | Part 2 | the "Initiated By" or the "Reason for Change"
Both the "Initiated By" and "Reason for Change" | [7 empty] | fields have not been completed correctly.
Project Code |  |  | Change Order Number |  | Change Order Date |  |  | Both of these fields must be filled-in !
0 - 00000 - 000 |  |  | 0 |  | #N/A
PIMS #: | 0 |  |  |  | #N/A | #N/A
WO#: | 0 |  |  |  | Change Order Total (sum of the details listed below) = | 0
#N/A
#N/A
Reference |  |  |  | Initiated | Reason |  |  | Reason for Change
Number |  | Description |  | By | Code | Amount |  | (this entry updates the "Reason Code" column)
Use drop down box to select reason code
Codes are from 1 - 9

## Reason Codes (hidden)
Reason Code Legend:
1 - Unforeseen site conditions.
2 - Existing bldg or utility conditions not as shown.
3 - Change in agency program requirements
4 - Change for user requested enhancement
5 - Substitution or alternate method.
6 - Item not as shown or specified.
7 - Conflict or discrepancy in requirements.
8 – Planned Change
9 - Other. Describe below the Work Description.
Project Mgrs
Proj Mgrs Typed Name
Shannon Barras
Annette Cyphers
Steve Dempsey
Amy Eichenberger
Craig Hilten
Joseph Lahendro
Kate Meyer
Steve Nelson
David A. Paley
Charlotte P Dickerson
Randall Porter
Lynn Rush
William H.Shirey, Jr.
Ryan Taylor
James D.W. Zehmer
Mashal Afredi
Frederick Dunn
D. Andrea Fraley
Mark Humbertson
Dana Hodges
James A. Loman
William Moore
Brian Pinkston
Christian Pouncey
Joseph Rainwater
Stephan Rohr
Tim Roland
P. Kevin Silson
Michael Vanderweide
Kristine C. Vey
David (Derek) Wilson
Eugenio Schettini
William Blodgett
Zachary Brackett
Charles (Mike) Garascia
Taryn Harrison
Joseph Phillips
Melanie S. Marshall-Roth
David Villiott

## HECO-11a_Part 1
|  |  | CHANGE ORDER JUSTIFICATION |  |  |  | HECO-11a
(Rev. 08/31/12) |  |  | ( Architect / Engineer's Justification ) |  |  |  | Part 1
Project Code |  |  | Change Order Number |  | Change Order Date
0 - 00000 - 000 |  |  | 0 |  | #N/A
PIMS #: | 0 | WO#: | 0
A/E's DESCRIPTION OF WORK INVOLVED
A/E's EXPLANATION OF WHY WORK IS REQUIRED
A/E's RECOMMENDATION
A/E's RECOMMENDATION
|  |  |  | Architect / Engineer |  | Date
Select appropriate recommendation using drop-down box.

## HECO-11a_Part 2
|  |  | CHANGE ORDER JUSTIFICATION |  |  | HECO-11a
(Rev. 08/31/12) |  |  | ( Project Manager's Justification ) |  |  | Part 2
Project Code |  |  | Change Order Number |  | Change Order Date
0 - 00000 - 000 |  |  | 0 |  | #N/A
PIMS #: | 0 | WO#: | 0
ADDITIONAL CONTINGENCY REQUIRED ?
Remarks:
COST SHARING FOR DESIGN ERRORS AND OMISSIONS
Is this change order required in whole, or in part, because of a design error of omission?
If "Yes", was any rework required? If yes, outline the proposed cost sharing, if any, by the responsible design professional:
ADDITIONAL SUPPORT FOR CHANGES
1) What quantitative impact would the lack of this change have on the mission or service provided by the agency?
2) Is the cost for the change reasonable? (Include if price was revised and if consistent with independent estimate.)
3) Is sufficient contingency available for this change? |  |  |  | Also where applicable, use of contingency funds has been approved
By: |  |  |  | Proj Mgrs Typed Name
| Project Manager |  |  |  | Date
Note on F57: Pls use drop down box
* See drop down box w/ printed mgrs typed name
* Signature is also required
* By signing, Project Mgr is signifying that
sufficient contingency is available.

## HECO-11a_Part 3
No direct data entry is required on this sheet, however, verify the total is correct. If the total is incorrect, return
to the "CO-11 Part 2" sheet and ensure that all lines with an "Amount" have a corresponding "Reason Code".
|  |  | CHANGE ORDER JUSTIFICATION |  |  |  | HECO-11a
(Rev. 08/31/12) |  |  | ( Statistical Summary ) |  |  |  | Part 3
Project Code |  |  | Change Order Number |  |  | Change Order Date
0 - 00000 - 000 |  |  | 0 |  |  | #N/A
PIMS #: | 0 | WO#: | 0
Reason
| Code | Amount |  |  | Reason Code Description
| 1 | 0 |  | 1 - Unforeseen site conditions
| 2 | 0 |  | 2 - Existing building or utility conditions not as shown
| 3 | 0 |  | 3 - Change in agency program requirements
| 4 | 0 |  | 4 - Change for user requested enhancement
| 5 | 0 |  | 5 - Substitution or alternate method
| 6 | 0 |  | 6 - Item not as shown or specified
| 7 | 0 |  | 7 - Conflict or discrepancy in requirements
| 8 | 0 |  | 8 – Planned Change (Additive Bid/Price Items, VM Items, Final Design Bulletins, Etc.)
| 9 | 0 |  | 9 - Other.
| Total | 0
Criteria Fields for DataSum Operation Above
(do not delete these entries)
Code
1
Code
2
Code
3
Code
4
Code
5
Code
6
Code
7
Code
8
Code
9