State of Minnesota

<project name> Project

Monthly Status Report (Example)

Project Name:	Example Project 	Reporting Period:	November, 2004

Project Manager:	Name, Title

Project Owner:	Name, Title

Project Sponsor:	Name, Title

Executive Summary

##### Overall Status:	 Yellow

|  | ### Green ### (Controlled) | ### Yellow ### (Caution) | ### Red ### (Critical) | ### Reason for Deviation |
| --- | --- | --- | --- | --- |
| Budget |  |  |  |  |
| Schedule |  |  |  | Deliverable XYZ delayed |
| Scope |  |  |  | External project deliverable strategy being redefined |

##### Comments:

- Definition of the XYZ deliverable needs to be finalized.  Content is currently being generated.  This important deliverable will need to be reviewed and updated for high quality.

Controls

##### Issue Status:

- A strategy needs to be established and agreed upon relative to responding to requests for information associated with the project.  This issue is being worked.

##### Change Status:

- XYZ deliverable due date changing from 3/7/2005 to 3/21/2005.

##### Risk Status:

- Risk: There is risk that the project accomplishments could lose their impact and the needed momentum for the follow-on effort could be minimized if a transition plan to the next phase is not defined and executed.

Mitigation:  The following two activities are being initiated:

- A communications plan is being developed and executed to support the involvement of the Governor’s office and related legislative sponsorship.

- A program portfolio for the follow-on effort is being generated. A transition work plan will capture the recommendations of the project. Follow-on project initiatives will be developed based on the recommendations of the project.

Budget

Budget Status as of 10/31/2004

Budgetary Comments:

- Burden rate of $100 per hour assumed for internal resources

- Spent to date is estimated based on a linier prorated over time algorithm

- Internal budget does not include steering committee member resources

- Increase in internal current budget is due to two additional weeks of deliverable generation

- Internal budget includes state resources deployed on the effort

Scheduled Milestones / Deliverables

| Milestone | Approved Schedule | Current Forecast | Actual | Status |
| --- | --- | --- | --- | --- |
| Start Project | 6/1/2004 |  | 6/1/2004 | Complete |
| Vendor RFP posted | 6/19/2004 |  | 6/19/2004 | Complete |
| Vendor selected | 7/21/2004 |  | 8/8/2004 | Complete |
| Vendor contract awarded | 9/1/2004 |  | 9/25/2004 | Complete |
| Program resources identified |  | 9/9/2004 |  | Complete |
| Steering Committee identified |  |  |  | Complete |
| Phase I kick-off | 10/8/2004 | 10/13/2004 | 10/13/2004 | Complete |
| Communications Plan available | 10/10/2004 |  | 10/10/2004 | Accepted |
| Activity completed | 12/8/2004 |  | 12/8/2004 | Complete |
| Activity completed | 12/8/2004 |  |  | Complete |
| Activity completed | 12/8/2004 | 12/15/2004 | 12/15/2004 | Complete |
| DEF Deliverable available | 12/29/2004 |  | 12/29/2004 | Accepted |
| GHI Deliverable available | 12/29/2004 |  | 120/29/2004 | Accepted |
| Phase II kick-off meeting | 1/1/2005 |  | 1/1/2005 | Complete |
| Phase III kick-off meeting | 1/6/2005 |  | 1/6/2005 | Complete |
| JKL Deliverable available | 2/3/2005 | 2/17/2005 |  | In Review |
| XYZ Deliverable available | 3/7/2005 | 3/21/2005 |  | Redefined |
| Records Retention Plan executed | 3/30/2005 |  |  | Yellow |
| Project complete | 3/31/2005 |  |  | Green |

Note: Bold milestones are key external project deliverable

Accomplishments & Plans

Accomplishments during this Reporting Period:

- Continued to execute the communications plan.

- Held several steering committee meetings.  Reviewed and approved deliverable

- Subcommittee of the Steering Committee evaluated and categorized recommendations and opportunities.

- Developed a work plan to schedule final update, review and acceptance of the project deliverable.

- Plans for the next Reporting Period:

- Develop, review and accept the XYZ deliverable.

- Review, update and accept all the vendor deliverable.

- Organize and archive all project materials.

- Execute the Records Retention plan.

- Start to initiate a transitional communications plan and program portfolio for the next steps that can be handed off to the program office that will be recommended by the project.

- Continue to maintain the project control practices – steering committee meetings, status reporting, issues management, change control, work plan, budget management, document management and risk management.

Project Definition

##### Project Description

This section contains a brief description of the business need that drives the project. The project will accomplish the following activities to support this vision:

- Broad description of activity

- Broad description of activity

##### Project Definition

| ## Business Objectives | - Providing modern, comprehensive and user-friendly electronic access to government program. - Decreasing the administrative cost of providing the service while increasing the quality and efficiency. |
| --- | --- |
| ## Scope | - Identify business transactions performed by the program, documented in the form of a current business process model - Identify information requirements of the business transactions performed by the program, documented in the form of a data flow diagram - Identify technologies used by the program, documented in the form of a current technology model - Identify potential opportunities to improve efficiency and effectiveness through the use of streamlined processes, |
| ## Assumptions | - The program’s resources meet the requirements (skills, experience and time commitment) specified in the “Roles and Responsibilities” and “State FTEs” attachments to the Statement of Work. - Existing procedural and system documentation for all in-scope businesses and systems will be available to the project team very early in the project. - The approach to this project is based on the vendor’s methodology for organizational performance enhancement. - It will be the State’s responsibility to review, verify, and confirm the accuracy of the data provided to the project team by each agency. |
| ## Dependencies | - The Governor’s budget process - Constraints governed by the Data Practices Act - Constraints inherent in an aggressive project schedule |